## Agile Strategy
Streamlining Banking Support Operations: Agile Strategy
Proposed approach aligned to the Jira epics and user stories
Area | Strategy | Application to This Project | Evidence / Output
Agile approach | Use Scrum with time-boxed sprints and a prioritised backlog. | Plan four two-week sprints, with one primary epic addressed per sprint. | Jira backlog and sprint boards
Backlog structure | Group related requirements into epics and break them into user stories. | Four epics containing nine user stories; acceptance criteria are recorded in each story description. | Jira epics and user stories
Prioritisation | Prioritise work by operational importance and dependency. | High priority: request intake, tracking, resolution, ownership, escalation, knowledge and workflow. Medium priority: reporting and continuous improvement. | Jira priority fields
Sprint planning | Select the stories that support the sprint goal and fit the sprint timebox. | Assign the stories for each epic to its corresponding sprint; keep sub-tasks under their parent stories. | Sprint backlog and sprint goals
Execution and tracking | Track each story through To Do, In Progress and Done. | Update story and sub-task statuses as work progresses; review blockers and remaining work. | Jira Scrum board
Review | Review completed work against acceptance criteria at the end of each sprint. | Confirm that each story's acceptance criteria are met before marking it Done. | Completed stories and review notes
Retrospective / improvement | Identify what worked, what did not, and one improvement for the next sprint. | Record brief improvement actions after each sprint and apply them to the next sprint. | Retrospective notes / improvement actions
Definition of Done | Work is complete when acceptance criteria are met and the outcome is documented. | Relevant story/sub-task statuses are updated and supporting evidence is captured where applicable. | Done status and project evidence
Planning assumptions | Dates and sprint allocation are proposed planning choices, not specified by the original project guidelines. | Sprint 1: 26 Oct–6 Nov 2026; Sprint 2: 9–20 Nov 2026; Sprint 3: 23 Nov–4 Dec 2026; Sprint 4: 7–18 Dec 2026. | Jira sprint configuration