## Release Roadmap
Streamlining Banking Support Operations: Release Roadmap
Proposed roadmap based on the project's four-epic, four-sprint plan.
Release / Milestone | Planned Dates | Epic / Focus | Included User Stories | Expected Outcome | Completion Evidence
Release 1 — Structured Support Requests | 26 Oct–6 Nov 2026 (Sprint 1) | Support Request Management | US1 Submit a Support Request; US2 Track Support Request Status; US3 Record Resolution and Close Request | A defined process for submitting, tracking, resolving, and closing support requests. | Jira stories and acceptance criteria; Sprint 1 board/backlog screenshots; wireframes related to request handling.
Release 2 — Ownership and Escalation | 9–20 Nov 2026 (Sprint 2) | Application Ownership and Escalation | US4 Identify Application Owner; US5 Escalate Unresolved Issues with Context | Clear application ownership and a documented escalation process for unresolved issues. | Jira stories and acceptance criteria; updated workflow / experience-map artefacts.
Release 3 — Knowledge and Standardised Processes | 23 Nov–4 Dec 2026 (Sprint 3) | Knowledge and Standardised Processes | US6 Find Approved Support Procedures; US7 Standardise Support and Escalation Workflow | Support procedures are easier to locate and the support workflow is more consistent. | Jira stories and acceptance criteria; knowledge/process wireframes or diagrams.
Release 4 — Reporting and Continuous Improvement | 7–18 Dec 2026 (Sprint 4) | Reporting and Continuous Improvement | US8 View Basic Support Activity; US9 Review Outcomes for Process Improvements | Basic support activity can be reviewed and outcomes can inform process improvements. | Jira stories and acceptance criteria; reporting requirements and final project recommendations/reflection.
Planning note: The dates and release sequence are proposed planning assumptions, not dates prescribed by the original project guidelines. Outcomes describe intended deliverables, not evidence that a release has already been completed.