## Sprint Delivery Matrix
STreamlining Banking Support Operations: Sprint Delivery Matrix
Proposed sprint-level view of planned work, outputs, and completion checks.
Sprint / Dates | Epic | User Story | Priority | Planned Delivery / Task | Acceptance / Completion Check | Evidence / Output
Sprint 1 26 Oct–6 Nov 2026 | Support Request Management | US1 — Submit a Support Request | High | Define the support request submission flow and required fields. | A user can submit a request with the required information; criteria are testable in the Jira story. | Jira story, acceptance criteria, related wireframe.
Sprint 1 26 Oct–6 Nov 2026 | Support Request Management | US2 — Track Support Request Status | High | Define request statuses and how a user checks progress. | Request status is visible and understandable against the criteria recorded in Jira. | Jira story, acceptance criteria, status/tracking wireframe.
Sprint 1 26 Oct–6 Nov 2026 | Support Request Management | US3 — Record Resolution and Close Request | High | Define resolution details and request-closure requirements. | Resolution can be recorded and the request closed according to the Jira criteria. | Jira story, acceptance criteria, closure workflow.
Sprint 2 9–20 Nov 2026 | Application Ownership and Escalation | US4 — Identify Application Owner | High | Document how support staff identify the responsible application owner. | The responsible owner can be identified using the requirements recorded in Jira. | Jira story, acceptance criteria, ownership flow.
Sprint 2 9–20 Nov 2026 | Application Ownership and Escalation | US5 — Escalate Unresolved Issues with Context | High | Define escalation steps and the context passed with an unresolved issue. | An unresolved issue can be escalated with the required context as defined in Jira. | Jira story, acceptance criteria, escalation workflow.
Sprint 3 23 Nov–4 Dec 2026 | Knowledge and Standardised Processes | US6 — Find Approved Support Procedures | High | Document requirements for finding approved support guidance. | A support user can locate the relevant approved procedure according to Jira criteria. | Jira story, acceptance criteria, knowledge-access wireframe.
Sprint 3 23 Nov–4 Dec 2026 | Knowledge and Standardised Processes | US7 — Standardise Support and Escalation Workflow | High | Document a consistent support and escalation workflow. | The workflow clearly defines the expected support and escalation steps. | Jira story, acceptance criteria, process diagram.
Sprint 4 7–18 Dec 2026 | Reporting and Continuous Improvement | US8 — View Basic Support Activity | Medium | Define basic support activity reporting needs. | The required activity information is specified and reviewable against Jira criteria. | Jira story, acceptance criteria, reporting requirements.
Sprint 4 7–18 Dec 2026 | Reporting and Continuous Improvement | US9 — Review Outcomes for Process Improvements | Medium | Define how outcomes are reviewed to identify improvements. | A review process captures outcomes and potential improvements as defined in Jira. | Jira story, acceptance criteria, improvement-review requirements.
Planning note: Sprint dates are proposed assumptions. Completion checks should be aligned with the acceptance criteria actually saved in Jira; this matrix is a planning aid, not proof that the work has been completed.