## Sprint Plan
Streamlining Banking Support Operations : Sprint Plan
Proposed four-sprint plan; each sprint is two weeks. Dates are planning assumptions, not specified in the original project guidelines.
Sprint | Planned Dates | Epic | Sprint Goal | User Stories | Planned Deliverables | Dependencies / Notes
Sprint 1 | 26 Oct–6 Nov 2026 | Support Request Management | Establish a structured support request process covering submission, status tracking, resolution, and closure. | Submit a Support Request; Track Support Request Status; Record Resolution and Close Request | Documented request fields and submission requirements; defined statuses and tracking requirements; resolution and closure requirements. | Complete the three stories and their sub-tasks within the sprint; validate against acceptance criteria.
Sprint 2 | 9–20 Nov 2026 | Application Ownership and Escalation | Define application ownership and clear escalation procedures for unresolved issues. | Identify Application Owner; Escalate Unresolved Issues with Context | Documented ownership requirements; escalation requirements and procedures. | Build on the request-tracking process from Sprint 1.
Sprint 3 | 23 Nov–4 Dec 2026 | Knowledge and Standardised Processes | Establish accessible support documentation and a standardised support workflow. | Find Approved Support Procedures; Standardise Support and Escalation Workflow | Documented support knowledge requirements; documented standard support workflow ready for stakeholder review. | Use ownership and escalation responsibilities defined in Sprint 2.
Sprint 4 | 7–18 Dec 2026 | Reporting and Continuous Improvement | Define basic support reporting and a process for reviewing outcomes and identifying improvements. | View Basic Support Activity; Review Outcomes for Process Improvements | Documented reporting requirements and measures; documented process-improvement review requirements. | Use request statuses and workflow definitions from earlier sprints.